## Security
# | Project / Workstream | Status | RAG Status | Start Date | Completion Date | % of Completion | Core Objective | Current Progress | Key Next Steps | Owners / Direct Responsible Individual | Key Risks / Blockers | Management Attention | Source / Notes
1 | PCI Payment Data Environment | Scope Review | Amber | TBD | TBD | 25% | Map PAN / CVV / token data flows. | Card data confirmed to pass through the payment gateway front/back end. | Confirm data flow, storage, encryption, logging, and related controls. | Mike Wang, Robert | Actual PAN/CVV processing scope. | Align with SAQ-D. | User-provided project table
2 | Web Security | In Progress | Amber | TBD | TBD | 50% | Provide web security protection for UNIS and ITEM SaaS servers. | AWS, Fortinet, Cloudflare, and Palo Alto have been tested. | Issue test report, obtain quotations, and submit purchase request. | Mike Wang, Robert | Business impact and cost/compliance requirements. | Requires selection and procurement decision. | User-provided project table
3 | DNS Security | In Progress | Amber | TBD | TBD | 50% | Deploy DNS security across branches to supplement endpoint security. | China uses OneDNS free tier; overseas uses Cloudflare free security DNS; Infoblox and Palo Alto DNS security tested. | Issue test report, obtain quotations, and submit purchase request. | Mike Wang, Robert | Cost; phased branch rollout required. | Select key branches and phase deployment. | User-provided project table
4 | Security Awareness & Incident Response | Roadmap | Amber | TBD | TBD | 35% | Reduce human-factor security risk | All employees training and set up phishing simulations | 1. Phishing simulations 2. Security training sessions 3. Incident response drills | Mike Wang, Robert | See project scope/tasks and dependencies. | Priority: N/A; Target: Q2 | Uploaded IT_Project_Roadmap_2026.xlsx
5 | Network MFA Rollout | Pilot Testing / In Progress | Amber | TBD | TBD | 75% | Protect SSL VPN and FortiGate administrator access with MFA. | VPN MFA documentation is complete and pilot users have been added; administrator MFA through Microsoft remains under investigation. | Complete pilot testing and implement the approved administrator MFA method. | Jerimar Castaneda / IT Team | Administrator access remains dependent on an unconfirmed MFA design. | Confirm method and rollout date. | IT Network Team Meeting Notes, 11-Sep-2026 PST
6 | Ticket 23527 Monitoring Access Review | Authorization Review | Amber | TBD | TBD | 20% | Migrate Olly Chen's monitoring environment while enforcing least privilege. | The request covers migration from AWS to ITEM and management of assigned Raspberry Pi and robotics devices; ownership and authorization are not yet documented. | Identify named users, approved activities, approving authority, and the exact device group; configure group-restricted access. | Mel Gutierrez / China Engineering / Olly Chen / Approver | Broad access could expose devices belonging to other groups. | Do not grant unrestricted access; require an approved access matrix. | IT Network Team Meeting Notes, 11-Sep-2026 PST; Ticket 23527
7 | Windows 10 Security Remediation | Inventory / Compatibility Review | Amber | TBD | TBD | 20% | Remove unsupported Windows 10 exposure without disrupting robotics operations. | The endpoint population is not yet known; Mel can export the inventory from the current remote-management platform. | Export inventory, test application compatibility, prioritize endpoints, and approve phased upgrade or replacement. | Mel Gutierrez / Robert Moreno / Mike Wang / Robotics Team | Unsupported endpoints create cybersecurity risk; incompatible upgrades could interrupt operations. | Review risk-ranked inventory and remediation plan. | IT Network Team Meeting Notes, 11-Sep-2026 PST
8 | Dedicated Teams Room PC Security | Security Review / In Progress | Amber | TBD | TBD | 35% | Enable persistent Teams-room use with an accountable licensed identity and secure unattended configuration. | SBW1153 was removed from the domain and currently uses a passwordless local UNIS account. | Create a dedicated licensed Microsoft account; document device ID, location, owner, users, configuration, and support ticket; apply unattended-use controls. | Mel Gutierrez / Jesse Webb / Armin / Business Owner | A passwordless local account creates unattended-login and accountability risk. | Approve the dedicated-account and endpoint-control design. | IT Network Team Meeting Notes, 11-Sep-2026 PST
9 | Amazon SP-PII Security Certification 2026 | Submitted / Pending Review | Amber | 2026-08-27 | TBD | 100% | Complete the annual Amazon SP-PII certification through formal reviewer acceptance. | All 138 tasks are complete and were submitted on 14-Sep-2026 for initial review; no current risks were identified. | Monitor review, answer evidence requests, remediate findings, obtain final confirmation, and retain the annual evidence baseline. | Qingmin Li / Robert Moreno / Linker Department | Reviewer findings may require additional evidence before closure. | Track initial-review and final-acceptance dates. | IT Network Team Meeting Notes, 11-Sep-2026 PST; submission update 14-Sep-2026

## Infrastructure & Cloud
# | Project / Workstream | Status | RAG Status | Start Date | Completion Date | % of Completion | Core Objective | Current Progress | Key Next Steps | Owners / Direct Responsible Individual | Key Risks / Blockers | Management Attention | Source / Notes
1 | QTS Data Center Service Reactivation | Pending / GO Recommended | Green | TBD | TBD | 75% | Reactivate QTS and transition it to UNIS service. | IT confirmed a clear business and technical need. | Complete QTS financial reconciliation and obtain the UNIS agreement. | Mike Wang, Robert, Network Team | Contract, cost, duplicate billing, service reactivation. | GO recommended. | User-provided project table
2 | QTS Central U.S. Regional Hub | Strategic Direction | Green | TBD | TBD | 75% | Establish a Central U.S. regional infrastructure hub. | Confirmed it can reduce latency for Central/East warehouses to West Coast data centers. | Plan AD, HikCentral, application servers, network, and related infrastructure. | Mike Wang, Robert, Network Team | Build and operating cost. | Include in long-term U.S. data center architecture. | User-provided project table
3 | Atlanta 6150 LaGrange Internet | In Progress | Green | TBD | TBD | 85% | Provide connectivity to support the new Atlanta warehouse launch. | Permanent AT&T circuit estimated at ~60 days; SkyLink and AT&T Wireless temporary options being evaluated. | Test temporary options onsite and select the transition solution. | Mike Wang, Robert, Network Team | AT&T delivery timeline may affect warehouse launch. | P1 | User-provided project table
4 | 6150 LaGrange Network Design | Completed | Green | TBD | TBD | 100% | Complete the standard network architecture. | Phase 2 overall design direction is OK. | Complete the initial network plan using the standard template. | Mike Wang, Robert, Network Team | Hardware / Internet approval. | Initial review must be completed first. | User-provided project table
5 | 6150 LaGrange Wi-Fi / Heatmap | Completed | Green | TBD | TBD | 100% | Complete Wi-Fi coverage and capacity design. | Phase 2 planning underway. | Complete heatmap and final connectivity / port mapping. | Mike Wang, Robert, Network Team | Equipment arrival and final design. | Manage together with new-site network design. | User-provided project table
6 | ISP / Circuit Optimization | Ongoing | Green | TBD | TBD | 75% | Optimize U.S. ISP cost and circuit portfolio. | Multiple circuits are being migrated, disconnected, or renewed; Garden City, Suffolk, Torrance, Norcross and others are involved. | Continue circuit reviews, migrations, disconnects, and renewals. | Mike Wang, Robert, Network Team | Long-term circuit contracts and ETFs. | Continue reducing recurring cost. | User-provided project table
7 | Atlanta / Network Standardization | In Progress | Green | TBD | TBD | 75% | Establish a standard new-site network process. | Unified network planning template has been required. | Template → review → detailed design → implementation. | Mike Wang, Robert, Network Team | Skipping design review increases implementation risk. | Use as standard process for all new sites. | User-provided project table
8 | Wireless Survey Tools | In Progress | Green | TBD | TBD | 75% | Provide appropriate wireless survey tools for Network and Installer teams. | NetAlly and Ekahau have been tested. | Purchase both: NetAlly for Installer Team and Ekahau for Network Team; proceed with purchase request. | Mike Wang, Robert, Network Team | User training and cost. | Proceed with procurement. | User-provided project table
9 | Alessandro – Wi-Fi (Docks 55–75) | In Progress | Green | TBD | TBD | 100% | Restore stable Wi-Fi coverage around Docks 55–75. | APs are online and Aruba APs were restarted, but weak/dark areas remain. Recent data drops are packing PCs and hardwired TSC printers and are not currently believed to be the cause. | Onsite physical inspection for coverage, physical changes, and interference. | Mike Wang, Robert, Network Team | Warehouse operational impact if degradation continues. | Escalate if physical inspection cannot identify the cause or additional AP coverage is required. | 8/19 status update
10 | Long Beach – Backup Connectivity | Evaluation | Green | TBD | TBD | 100% | Provide additional backup connectivity if temporary AT&T capacity is insufficient. | Skylink/satellite discussed; availability/performance need validation and prior Atlanta experience was mixed. | First validate two AT&T gateways; evaluate Skylink only if additional capacity is required. | Mike Wang, Robert, Network Team | Temporary solutions may not support full-site traffic. | Decision only if AT&T capacity is insufficient. | 8/19 status update
11 | Atlas / Camera Access Security | Security Risk | Green | TBD | TBD | 100% | Ensure camera access follows least privilege and role-based permissions. | Potential over-broad camera visibility for company-credential users; HikCentral/domain synchronization has missing users and permission-sync issues. | Validate exposure, correct access controls/domain sync, and provide remediation timing. | Mike Wang, Robert, Network Team | Unauthorized or excessive camera visibility. | Confirm owner, remediation ETA, and temporary access restrictions if needed. | 8/19 status update
12 | Stimson – Power Panel Upgrade | Approved / Pending Schedule | Amber | TBD | TBD | 70% | Upgrade the site power panel. | Technical specification confirmed and Adam approved; procurement/execution expected through Cubework/local electrician. | Mahan to follow up with Jorge/Cubework and confirm purchase and installation schedule. | Mike Wang, Robert, Network Team | Planned downtime and facility coordination. | Confirm procurement owner, installation date, and outage window. | 8/19 status update
13 | Buena Park – Conference Room | Pending Maintenance Window | Green | TBD | TBD | 100% | Troubleshoot the conference room issue. | Troubleshooting has not started because the room is continuously occupied. | Coordinate a dedicated maintenance window. | Mike Wang, Robert, Network Team | Issue remains unresolved. | Local office assistance may be needed to reserve the room. | 8/19 status update
14 | LaGrange, Atlanta – Field Network Activities | Paused / Monitoring | Green | TBD | TBD | 100% | Maintain temporary connectivity and complete remaining LaGrange activities. | Temporary hotspot moved to MDF; UniFi devices should be online. Field work paused while resources support Douglasville. | Monitor temporary connectivity; resume after Douglasville decommission. | Mike Wang, Robert, Network Team | Resource shift may delay work. | No immediate escalation. | 8/19 status update
15 | MDM Migrate to ManageEngine Endpoint Central | In Progress | Amber | TBD | TBD | 60% | Advance Apple Business / MDM case. | No significant update received; lower priority than Willow/Douglasville. | David to follow up with Apple Business after higher-priority field activities. | Mike Wang, Robert, Network Team | Competing field priorities may delay progress. | Escalate existing case if required. | 8/19 status update
16 | Walnut Migration | In Progress | Green | TBD | TBD | 100% | Complete remaining Walnut server/DMZ migration work. | No broader outstanding firewall initiative; remaining work is primarily Walnut server/DMZ migration. | Complete migration and validate final configuration. | Mike Wang, Robert, Network Team | Low if migration completes as planned. | Confirm closure criteria. | 8/19 status update
17 | Walnut – Network Work | Pending Equipment | Green | TBD | TBD | 100% | Complete required Walnut network work. | Cable received; GBIC/SFP remains the dependency. | Confirm GBIC arrival and proceed onsite when all equipment is available. | Mike Wang, Robert, Network Team | Equipment delay. | Proceed once GBIC is available. | 8/19 status update
18 | Walnut DC Network Optimization | Roadmap | Green | TBD | TBD | 100% | Establish a standardized, manageable, and reliable DC network Optimize VLANs and IP addressing for performance and security Replace non-standard/legacy switches with uniform models to simplify operations Improve camera network performance for stable, low-latency video transmission Deliver standardized cable management, network documentation, and operational guidelines Prepare the network for production deployment and potential multi-region implementation | Conduct a comprehensive network optimization for Walnut Data Center, including: Cable management and rack organization Replacement of non-standard/outdated switches VLAN and IP address planning and optimization CCTV / camera network optimization Improve network performance, manageability, and scalability Enhance network troubleshooting efficiency and security | Evaluate existing network, devices, and rack conditions; define optimization plan Organize and standardize data center cabling Replace non-standard switches and configure new devices Replan VLANs and IP addressing for efficiency and manageability Optimize camera VLANs, PoE, and bandwidth allocation Update network topology, IP plan, and SOPs; validate optimization results Plan production-grade deployment and multi-region expansion | Mike Wang, Robert, Network Team | See project scope/tasks and dependencies. | Priority: N/A; Target: Q2 | Uploaded IT_Project_Roadmap_2026.xlsx
19 | UNIS.CO Email Transition & Ticketing Integration | In Progress / Seven Exceptions | Amber | 2026-08-06 | TBD | 90% | Complete the UNIS.CO transition and confirm reliable mailbox and ticketing readiness. | Core controls are implemented; four UPN/email mismatches and three non-unis.co accounts remain, along with final workflow checks. | Correct and revalidate the seven accounts and close OTP, shared-mailbox, monitoring, and business-readiness evidence. | Robert Moreno / Mike Wang / Lex Yang / Yangyang Yang / Mel Gutierrez / Gemar Ermac / Billy Rivas | Unresolved exceptions or workflow failures could disrupt access and operations. | Require verified closure evidence before sign-off. | IT Network Team Meeting Notes, 11-Sep-2026 PST
20 | Davao SFTP Server Request | Requirements / Approval Pending | Amber | TBD | TBD | 15% | Securely deliver the requested SFTP capability in Davao. | The technical team is awaiting the complete request reportedly sent by Chi wei to Mike. | Confirm owner, hosting, IP allowlisting, authentication, data scope, logging, retention, test window, and success criteria. | Robert Moreno / Mike Wang / Chi wei / Jerimar / Peng Gao / Mel Gutierrez | Incomplete architecture and approvals could cause delay or insecure public exposure. | Require written requirements and security approval before configuration. | IT Network Team Meeting Notes, 11-Sep-2026 PST
21 | Alessandro PDU Incident Remediation | Urgent / In Progress | Red | 2026-09-09 | TBD | 25% | Replace the failed-risk power distribution and protect WMS and sorter equipment. | Two systems were damaged after the 9-Sep power interruption; the suspect PDU remains live and powers six or seven computers. | Validate PDU/UPS electrical specifications, replace the PDU and cables in a controlled window, and assess an onsite spare workstation. | Mahan Sasani / David Rodriguez / Abhijeet / Brant Li, Robert, Mike W | Further surge damage or a poorly planned cutover could interrupt operations. | Urgent compatible-part approval and cutover coordination are required. | IT Network Team Meeting Notes, 11-Sep-2026 PST
22 | AP10 and Offline Device Remediation - 2131 Willow | Open / Troubleshooting | Amber | 2026-09-08 | TBD | 35% | Restore stable wireless performance and reconnect two offline devices. | AP10 showed approximately 23% TX retries; the abnormal condition cleared after reboot, but two devices have been offline since 8-Sep. | Jerimar to contact Efrain and coordinate with Mahan and Peng Gao to validate TX statistics and device status. | Jerimar Castaneda / Mahan Sasani / Peng Gao / Efrain | Offline devices and recurring TX retries may disrupt operations. | Confirm root cause, device recovery, and post-fix monitoring evidence. | IT Network Team Meeting Notes, 11-Sep-2026 PST
23 | Joliet New-Racking Wi-Fi and Pick-to-Light Readiness | In Progress / Input Pending | Amber | TBD | 2026-09-23 | 65% | Provide wireless coverage for new racking and support pick-to-light deployment. | The Wi-Fi survey is complete. AP installation targets 23-Sep; Veronica has not provided the final pick-to-light count and locations. | Complete AP installation and obtain the final device quantity and layout before deployment. | David Rodriguez / Veronica / Robert / Network Team | Late device-location input could delay go-live or require AP rework. | Escalate the final pick-to-light layout if it threatens the 23-Sep target. | IT Network Team Meeting Notes, 11-Sep-2026 PST
24 | Chicago 1333 Kingsbury Decommission | Urgent / In Progress | Red | TBD | TBD | 20% | Recover equipment and terminate services after the sales-office closure. | Site access may be limited or expired and onsite assets and ISP obligations remain unconfirmed. | Confirm access days, inventory and move assets to Buena Park, identify the ISP, disconnect service, and return equipment. | David Rodriguez / Raul / Erik Solis / Robert / Network Team | Asset loss and unmanaged carrier charges are possible if access is not restored quickly. | Immediate facility-access escalation is required. | IT Network Team Meeting Notes, 11-Sep-2026 PST
25 | Tolleson AZ Facility Decommission | Scheduled | Amber | 2026-09-21 | 2026-09-25 | 10% | Complete IT and network decommissioning before the 30-Sep building return. | David's team scheduled work for 21-25 Sep at 120 N 83rd Avenue. | Confirm access, asset and circuit inventory, logistics, equipment disposition, and closure evidence. | David Rodriguez / Network Team | Any delay could conflict with the building return date. | Maintain the scheduled window and confirm completion by 25-Sep. | IT Network Team Meeting Notes, 11-Sep-2026 PST
26 | MoFi Router and Mobile Hotspot Review | In Progress | Amber | TBD | TBD | 20% | Reconcile carrier hardware and services and remove unnecessary recurring cost. | The consolidated inventory is being prepared across all carriers; physical and business-use validation starts within the week. | Reconcile records; validate assignment, custodian, and need; document and complete approved returns, cancellations, reassignment, and billing closure. | Robert Moreno / David Rodriguez / Jerimar Castaneda / Mahan Sasani | Unknown device ownership and usage may conceal waste, loss, or operational dependency. | Keep the workstream open through final billing confirmation. | IT Network Team Meeting Notes, 11-Sep-2026 PST

## IoT
# | Project / Workstream | Status | RAG Status | Start Date | Completion Date | % of Completion | Core Objective | Current Progress | Key Next Steps | Owners / Direct Responsible Individual | Key Risks / Blockers | Management Attention | Source / Notes
1 | BP AI Camera IoT Phase 1 | Green / 8/20 Target | Green | TBD | TBD | 100% | Deploy AI cameras to production. | Monitoring Engine V2 and Backend API complete; iOS testing underway. | iOS → Security UAT → Go/No-Go. | Yabin Liu | UAT and critical defects. | P1 – 8/20 launch. | User-provided project table
2 | Walnut AI Camera IoT Phase 2 | Green / 8/28 Target | Green | TBD | TBD | 100% | Deploy intrusion, fight, fall, and crowd detection. | Camera scope and AI use cases are being defined. | Camera selection → algorithm mapping → GPU sizing. | Yabin Liu | Scope not frozen. | P2. | User-provided project table
3 | Walnut Local GPU Infrastructure | Green / 9/1 Target | Green | TBD | TBD | 100% | Completed note:Nearly one month of continuous monitoring shows GPU, memory and bandwidth metrics are fairly stable. The server also has 7×24 performance monitoring and alerting, so it is capable of running our existing system application architecture. | Preference is local GPU rather than using BP GPU. | Finalize GPU specifications and procurement after camera matrix completion. | Yabin Liu | GPU capacity, power, procurement ownership. | Local GPU recommended. | User-provided project table
4 | Warehouse Camera Network Health & Optimization Program | Green / 9/11 Target | Green | TBD | TBD | 100% | Ensure camera network stability, visibility, and operational accountability | Multiple warehouses reported offline / intermittently disconnected cameras, impacting security monitoring and compliance. All warehouse IP cameras, switches, VLANs, cabling, and PoE infrastructure | 1. Identify offline / unstable cameras per warehouse 2. Check PoE power budget and port utilization 3. Review cabling quality and labeling 4. Move cameras to dedicated Camera VLAN (remove from Default VLAN) 5. Replace faulty cables, connectors, or PoE injectors 6. Clean up IP conflicts and DHCP scope issues 7. Document per-warehouse camera topology | Yabin Liu | See project scope/tasks and dependencies. | Priority: N/A; Target: Q1-Q4 | Uploaded IT_Project_Roadmap_2026.xlsx
5 | User Manual Development (Monitoring Engine & IoT Platform) | Green / 9/11 Target | Green | TBD | TBD | 30% | In Progress | Finished drafting the 2/5 steps of the Monitoring Engine operation manual. | Completed the full operation manual for the Monitoring Engine. | Jiaming | Current Main Tasks for the IoT Platform‑ P2 Development | Target delivery: Sep 11 | Source note not provided.

## R&D AI
# | Project / Workstream | Status | RAG Status | Start Date | Completion Date | % of Completion | Core Objective | Current Progress | Key Next Steps | Owners / Direct Responsible Individual | Key Risks / Blockers | Management Attention | Source / Notes
1 | R&D / AI Project Portfolio Confirmation | Not Started | Amber | TBD | TBD | 0% | Confirm and document all active R&D and AI projects. | No projects were listed in the source workbook for this team. | Marco Ma, Olly, and Ken to provide the active project list, status, dates, progress, risks, and next steps. | Marco Ma / Olly / Ken | Incomplete project inventory may limit portfolio visibility. | Project list and ownership confirmation required. | Added based on Stacy's team-tab request.
2 | YMS Yard Check-In/Out Hardware and Software – Alessandro | In Progress | Amber | TBD | ETD: 4 weeks | 70% | Complete the hardware and software solution for the YMS yard check-in/check-out process. | Hardware and software implementation is 70% complete. | Complete the remaining integration, testing, and deployment activities. | Marco Ma / Olly | Final integration and validation activities are ongoing. | Continue monitoring overall progress and timeline. | YMS yard check-in/check-out project for Alessandro.
3 | Robot Dog B2W Deployment – Alessandro | Not Started | Amber | TBD | TBD | 0% | Complete the Robot Dog B2W deployment for Alessandro. | Deployment activities have not started. | Complete doghouse migration, site layout mapping, route design, and job design. | Marco Ma / Ken | Deployment planning and preparation are still in progress. | Continue reviewing project readiness and next-step planning. | Robot Dog B2W deployment for Alessandro.
4 | Loading Dock Safety Check | In Progress | Amber | TBD | ETD: 3–4 weeks | 40% | Develop an AI camera solution to improve safety monitoring at the loading dock. | Buena Park cameras have been installed. Algorithm development is in progress. | Complete algorithm development, conduct on-site testing, and validate detection accuracy. | Marco Ma / Olly | Additional testing and fine-tuning may be required. | Continue monitoring development and validation progress. | Buena Park camera installation completed.
5 | AGV Cycle Count in Bulk Area | In Progress | Amber | TBD | ETD: 2 weeks | 65% | Complete the AGV cycle-count workflow for the bulk area and prepare it for deployment. | Development and validation are 65% complete. | Complete validation and deploy the solution to Moreno Valley. | Marco Ma / Ken | Deployment activities may require additional coordination. | Continue monitoring deployment preparation and site coordination. | Target deployment site: Moreno Valley.
6 | IoT AI Camera Platform | In Progress | Amber | TBD | Ongoing / No ETA | 50% | Build and continuously improve a reusable IoT AI camera platform. | Platform development is 50% complete and remains ongoing. | Define the next development milestone and continue platform implementation and validation. | Marco Ma / Olly | Project scope and priorities may continue to evolve. | Continue reviewing milestones and overall project direction. | Ongoing project with no current ETA.
7 | ViT Library Maintenance for Packing Station | In Progress | Amber | TBD | TBD | 80% | Maintain and optimize the ViT library used by the packing station. | Library maintenance is 80% complete, with ongoing accuracy and performance improvements. | Continue accuracy improvement, performance optimization, and regression testing. | Marco Ma / Ken | Additional optimization and validation may be needed. | Continue monitoring accuracy and performance improvements. | ViT library maintenance for the packing station.
8 | Ticket 23527 Monitoring Platform Migration | Authorization / Design Review | Amber | TBD | TBD | 20% | Move Olly Chen's monitoring environment from AWS to ITEM with least-privilege device management. | The request includes Raspberry Pi and robotics devices, but named users, activities, approval authority, and device boundaries remain unclear. | Define the access matrix and migration owner; implement group-restricted access and validate separation before handover. | Olly Chen / Mel Gutierrez / China Engineering / Approver | Over-broad management access could expose devices outside Olly's assigned group. | Require explicit approval and device-group boundaries before provisioning. | IT Network Team Meeting Notes, 11-Sep-2026 PST; Ticket 23527
9 | Alessandro Dock Camera Expansion | Installation In Progress | Amber | TBD | 2026-09-30 | 70% | Complete approved dock-camera coverage before the operational deadline. | CAT6 is complete and power installation is in progress. Approved cameras target completion by the end of next week; five additional cameras remain unapproved. | Finish approved cameras, capture IP/MAC addresses, coordinate onsite angle tuning with the China development team, and obtain approval before starting the five additions. | David Rodriguez / Olly Chen / Marco Ma / CN Development Team | Power work, final angle tuning, or unapproved scope could affect the 30-Sep need. | Confirm completion and separately decide the five-camera expansion. | IT Network Team Meeting Notes, 11-Sep-2026 PST
10 | Heacock Yard Camera and Wireless Bridge | Layout / Approval Pending | Amber | TBD | TBD | 15% | Extend secure yard visibility to the rear guard-shack area. | Operations and Matthew requested a wireless building bridge and approximately four or five cameras on a concrete wall; layout is pending. | David to prepare the layout; confirm camera count, mounting, power, network path, bandwidth, approval, and installation schedule. | David Rodriguez / Matthew / Operations / Marco Ma | Unconfirmed layout and approval prevent accurate design and delivery timing. | Approve scope after layout and network feasibility review. | IT Network Team Meeting Notes, 11-Sep-2026 PST

## WCS Engineering
# | Project / Workstream | Status | RAG Status | Start Date | Completion Date | % of Completion | Core Objective | Current Progress | Key Next Steps | Owners / Direct Responsible Individual | Key Risks / Blockers | Management Attention | Source / Notes
1 | AirRob | Handed over to Ops team | Amber | TBD | TBD | 100% | Stabilize AirRob production operation and protect order-processing efficiency. | Operations is actively using the system. | Push the Ops team to put more SKUs in AirRob. | Brant Yi / Neil / Abhijeet / Anuj / WISE Team | Using the AirRob with limited current SKUs is using the AirRob with limited efficiency | No management update provided. | Project Update 8.xlsx – AirRob
2 | AGV-BP | Due to low volume of orders and not being used by the Ops team, the system is shifted from Production env to Preview Env. Now, this system will only be used for demo by the team. | Amber | TBD | TBD | 90% | Fix the AGVs so that it can be used properly for demo | Mapping and Validation done. | Push WISE team for logic improvement | Brant Yi / Neil / Abhijeet / Anuj / Network Team | Low order volume and limited Operations use may hide remaining issues until physical testing is completed. | Low priority | Project Update 8.xlsx – AGV-BP
3 | AGV-Memphis | At Risk / In Progress | Red | TBD | TBD (3-4 working weeks) | 50% | Validate the updated AGV software and complete camera-barcode implementation and final readiness testing in Memphis. | The AGV software has been updated following earlier testing issues. Abhijeet confirmed a three-to-four-working-week delivery plan: one week for initial testing, two weeks for camera-barcode implementation, and one week for final testing. | 1) Test the new AGV software update in the Memphis warehouse. 2) Based on results, decide whether reflector-based localization is required. 3) Modify the AGVs for camera-barcode scanning. 4) Complete final-readiness testing. 5) Coordinate network configuration changes or optimization if required. 6) Engage David's team if Abhijeet encounters issues modifying the AGV chassis. | Abhijeet / Robert / Brant Yi / Neil / Anuj / Network Team / David Rodriguez Team | Localization design is pending initial test results. Network changes may be required. Mechanical chassis modification may need David's team and could extend the timeline. | High priority: confirm the Memphis start date, test environment and orders, Network team support, reflector decision criteria, mechanical-support availability, and committed completion date. | Abhijeet AGV-Memphis update provided 14-Sep-2026 PST.
4 | Heacock – XYZ Palletizing Robot | Handed over to the ops team | Red | 2026-08-06 | TBD | 75% | Complete vision validation, real-container testing, operating controls, and safe production handover. | Small-batch validation is complete for 6 of 7 carton types. The robot has been handed over to the Operations team, who are now running it in production. The robot and conveyor remain temporarily aligned by floor markings and are not permanently anchored. | Expand the SKU set so the robot is not limited to a narrow range of cartons; monitor the trained Operations team on how they are running the robot day to day; revisit timing, cost, and ROI assumptions; determine the plan for the wrapping machine and pallet-movement conveyors. | XYZ Robotics / Anuj / Robert / Brant Yi / Neil / Abhijeet / UNIS Operations | Operations reports the robot is not currently delivering expected results. Downstream handling , wrapping and pallet movement is unresolved, and unanchored equipment may still shift and affect positioning and palletizing accuracy. | Confirm whether permanent anchoring will be completed before full production; if not, approve temporary controls, a responsible owner, and acceptance criteria before go-live. Review the ROI. Push Ops Team to use the robot. | XYZ Robotics status update as of 2026-08-16 PST; prior project update dated 2026-08-06.
5 | BP Conveyor Maintenance | Paused | Red | 2026-08-31 | TBD / Paused | 90% | Complete maintenance of the conveyor system and replace all spare parts ordered for the conveyor. | Maintenance is approximately 90% complete with one day of work remaining. | Obtain the correct roller and the remaining O-rings; schedule and complete the final day of maintenance; confirm conveyor operation before closure. | Anuj / Lafayette | The work is paused as the remaining materials delivered on site were wrong: roller is not compatible with the current system and the O-rings were short-shipped. Replacement materials are being sourced. | Need to process another 50% of the payment when the work is done. ( TBD - depending upon when we get the new roller from TGW ) | Source note not provided.
6 | VMS | Deployed / In Testing | Amber | 2026-07-31 | TBD (~3 days) | 80% | Deliver a seamless Visitor Management System. | The latest changes are deployed to the live site. Feature testing is ongoing to confirm expected behavior across the system. | Complete the remaining testing; release the system for general use; collect user-reported issues and feature requests and implement them as needed. | Anuj | AI Agent capability requested by Stacy, feasibility and implementation approach still to be evaluated. | Confirm the exact wording of customer-facing email and text notifications sent from the official UNIS account before general rollout. | Source note not provided.

## Johanson Group&Vanta Team
# | Project / Workstream | Status | RAG Status | Start Date | Completion Date | % of Completion | Core Objective | Current Progress | Key Next Steps | Owners / Direct Responsible Individual | Key Risks / Blockers | Management Attention | Source / Notes
1 | PCI DSS / SAQ-D | In Progress | Amber | TBD | TBD | 50% | Complete PCI DSS compliance. | atsec confirmed SAQ-D Merchant applicability. | Complete SAQ-D questionnaire, AOC, and technical scope confirmation. | Mike Wang, Robert, Johanson Group, Vanta Team | Large card-data scope. | P1 Compliance. | User-provided project table
2 | SOC 2 Type I Renewal | High Priority / Decision Pending | Red | 2026-08-03 | TBD | 65% | Complete the UNIS SOC 2 Type I renewal with sufficient evidence and auditor agreement on readiness. | E-waste pickup is complete with certificates due in three to four weeks; offboarding remains ongoing; planned and emergency change evidence is still awaiting Vincent. | Confirm parallel audit work and invoice timing with Adam G; obtain Vincent's evidence; validate recycling certificates. | Mike Wang / Robert Moreno / Adam G / Johanson Group / Vincent / David Rodriguez / Juan Cervantes | Outstanding evidence and unconfirmed readiness conditions may delay audit work. | Document the Johanson decision and committed evidence dates. | IT Network Team Meeting Notes, 11-Sep-2026 PST
3 | SOC 2 Type 2 Renewal for ITEM | In Progress | Amber | 2026-08-03 | TBD | 50% | Complete ITEM SOC 2 Type 2 renewal. | Scope has been defined. | Update scope and complete Vanta tasks. | Mike Wang, Robert, Johanson Group, Vanta Team | Evidence completeness and control execution consistency. | No management action required at this time | User-provided project table
4 | SOC 2 System / Application Scope | Scope Defined | Green | 2026-08-03 | TBD | 100% | Define the SOC 2 audit boundary. | UNIS SOC 2 Type I system/application scope is largely confirmed. | Convert scope into the final control/evidence matrix. | Mike Wang, Robert, Johanson Group, Vanta Team | Scope omissions or unclear boundaries. | Foundation for SOC 2 audit. | User-provided project table
5 | SOC 2 Control & Evidence Readiness | In Progress | Amber | 2026-08-03 | TBD | 50% | Prepare SOC 2 audit evidence. | Evidence work covers IT Operations, Security, Access, Change, Incident, and related areas. | Evidence collection → gap remediation → internal review. | Mike Wang, Robert, Johanson Group, Vanta Team | Insufficient evidence or inconsistent execution records. | Focus on actual execution, not policy only. | User-provided project table
6 | SOC 2 BCP / DR / Ticketing Continuity | High Priority | Red | 2026-08-03 | TBD | 50% | Ensure continuity of critical business systems. | Ticketing BCP/DR is a key production and audit dependency. | Complete BCP/DR plan, testing, and evidence. | Mike Wang, Robert, Johanson Group, Vanta Team | Ticketing outage may impact Customer Service. | Crosses SOC 2 and UNIS.CO. | User-provided project table
7 | GDPR Compliance Program | In Progress / Governance | Amber | 2026-08-03 | TBD | 50% | Establish GDPR privacy and data-protection framework. | Proposed as an independent compliance workstream in IT/Security governance. | Data Inventory → RoPA → DPIA → DPA → DSAR → Retention/Deletion → Security Controls. | Mike Wang, Robert, Johanson Group, Vanta Team | Personal-data scope and responsibility boundaries need confirmation. | P1 Compliance. | User-provided project table
8 | GDPR Data Inventory & RoPA | Not Fully Closed | Amber | 2026-08-03 | TBD | 100% | Identify personal data, purpose, location, and third parties. | Needs SaaS, logistics, customer, and employee systems review. | Build data inventory and Records of Processing Activities. | Mike Wang, Robert, Johanson Group, Vanta Team | Data is distributed across systems and regions. | GDPR foundation. | User-provided project table
9 | GDPR Data Transfer / Vendor Management | Review Required | Amber | 2026-08-03 | TBD | 25% | Manage cross-border data transfers and third-party processors. | US/China/other-region data flows and vendor relationships need confirmation. | Review DPA, SCC, sub-processors, and transfer mechanisms. | Mike Wang, Robert, Johanson Group, Vanta Team | Cross-border transfer compliance risk. | Integrate with vendor management. | User-provided project table
10 | GDPR DSAR / Data Subject Rights | Process Definition | Amber | 2026-08-03 | TBD | 25% | Support access, correction, deletion, restriction, and other data-subject requests. | Business and IT execution process needs definition. | Establish request intake → verification → system search → response. | Mike Wang, Robert, Johanson Group, Vanta Team | No unified process may cause response delays. | Consider integrating with ticketing. | User-provided project table
11 | GDPR Retention / Deletion | Policy / Implementation | Amber | 2026-08-03 | TBD | 50% | Establish personal-data lifecycle management. | Retention periods by system need to be determined. | Retention matrix → automated/manual deletion → evidence. | Mike Wang, Robert, Johanson Group, Vanta Team | Legacy data, backups, and third-party data. | Design together with Backup/DR. | User-provided project table
12 | UNIS SOC 2 Type I Open Evidence and Audit Decision | High Priority / Decision Pending | Red | 2026-08-03 | TBD | 65% | Close audit-readiness evidence gaps and obtain a documented decision on audit start and renewal payment. | E-waste pickup is complete, with certificates expected in three to four weeks. Offboarding continues as an ongoing control. Planned and emergency change evidence remains pending because Vincent has not responded. | Meet with Adam G to confirm parallel audit work, critical prerequisites, invoice timing, remaining owners, and dates; continue Vincent follow-up; validate recycling certificates when received. | Robert Moreno / Adam G / Johanson Group / Vincent / David Rodriguez / Juan Cervantes | Missing change evidence and unconfirmed auditor prerequisites may delay fieldwork; invoice timing remains unresolved. | Obtain Johanson's written readiness and payment decision and a committed date from Vincent. | IT Network Team Meeting Notes, 11-Sep-2026 PST
13 | UNIS and ITEM E-Waste Certification Evidence | Pending Vendor | Amber | 2026-09-10 | TBD (3-4 weeks) | 60% | Retain formal recycling evidence for audit and asset-disposal controls. | The vendor collected UNIS and ITEM equipment last Thursday; certificates are expected three to four weeks after pickup. | Track issuance, validate entity coverage, store certificates in the evidence repository, and link them to the applicable controls. | David Rodriguez / Recycling Vendor / Robert Moreno | Delayed or incomplete certificates could leave asset-disposal evidence unsupported. | Escalate if certificates are not received within the stated window. | IT Network Team Meeting Notes, 11-Sep-2026 PST
14 | Planned and Emergency Change Evidence | Pending Response | Red | TBD | TBD | 25% | Provide auditor-ready evidence that planned and emergency changes are authorized, tested, and recorded. | Robert followed up with Vincent by email and WeChat; Mike was copied, but no response has been received. | Vincent to provide evidence or a committed delivery date; Robert to continue follow-up and validate the submission with Johanson requirements. | Vincent / Robert Moreno / Mike Wang / Johanson Group | Missing evidence may delay readiness or fail auditor testing of the change-management control. | Escalate for a firm delivery date and confirm whether fieldwork can proceed in parallel. | IT Network Team Meeting Notes, 11-Sep-2026 PST

## UNIS.CO Email & Ticketing
# | Project / Workstream | Status | RAG Status | Start Date | Completion Date | % of Completion | Core Objective | Current Progress | Key Next Steps | Owners / Direct Responsible Individual | Key Risks / Blockers | Management Attention | Source / Notes
1 | UNIS.CO Internal-Only Email Restriction | Completed | Green | 2026-08-06 | TBD | 100% | Restrict individual UNIS.CO mailboxes to internal communication while preserving approved exceptions. | Core transport controls are implemented; external inbound and outbound traffic is restricted except for authorized users, domains, and mailboxes. | Maintain the approved exception list and include the control in operational change reviews. | Yangyang Yang, Robert, Mike Wang | An unauthorized policy change could reopen external mail flow or block approved business traffic. | No escalation required; retain change evidence and monitor exceptions. | Email thread: UNIS.CO Email Transition & Ticketing Integration, updated through 8-Sep-2026
2 | External Domain Allowlist Controls | Completed / Ongoing Governance | Green | 2026-08-06 | TBD | 100% | Permit legitimate external business traffic while maintaining the UNIS.CO restriction policy. | Approved customer and partner domains are supported; prior gaps such as newly identified domains showed the need for ongoing governance. | Use a documented onboarding and approval process for every new customer, partner, OTP, and system-notification domain. | Email Team / Operations / Yangyang Yang | A valid customer or partner domain may be rejected if it is absent from the allowlist. | Review blocked-message trends and escalate only validated business domains for approval. | Email thread: allowlist and external-domain validation updates through 8-Sep-2026
3 | Restricted Mailbox Bounce-Back Message | Completed | Green | 2026-08-06 | TBD | 100% | Give external senders clear instructions when an individual mailbox rejects their message. | Mary approved the revised customer-facing wording and the Email Team configured the bounce notification. | Retain the approved wording and periodically test delivery and clarity. | Gemar Ermac / Mary Smothers / Email Team | Incorrect routing guidance could delay customer inquiries. | No management action required unless testing identifies a failure. | Email thread: bounce-back wording approved and configured in Aug-2026
4 | Shared Mailbox and UnisTicket Workflow | In Progress / Final Confirmation | Amber | 2026-08-06 | TBD | 85% | Confirm that shared role/location mailboxes create and route tickets and that outbound replies reach customers. | Role/location mailboxes are already used with UnisTicket; formal end-to-end confirmation under the new mail-flow restrictions remains open. | Test inbound ticket creation, assignment, customer replies, attachments, and exception handling for representative business teams. | Lex Yang / Technical Team / Business Teams | A mail-flow rule could prevent ticket creation or block customer responses. | Close only after documented inbound and outbound test evidence is available. | Email thread: shared mailbox and ticketing confirmation requests through 8-Sep-2026
5 | Active PH Employee and Mailbox Inventory | In Progress / Seven Exceptions | Amber | 2026-09-01 | TBD | 90% | Ensure every active PH employee has the correct UNIS.CO or UNISCO.COM account disposition. | Yangyang completed the latest validation and found four UPN/email mismatches plus three accounts outside the unis.co domain. | Billy and Yangyang to correct the seven exceptions, revalidate the full list, and retain closure evidence. | Yangyang Yang / Billy Rivas / Mel Gutierrez / Gemar Ermac | Uncorrected accounts may cause access, routing, or migration omissions. | Track all seven exceptions to verified closure before full rollout. | IT Network Team Meeting Notes, 11-Sep-2026 PST
6 | OTP/MFA and System Notifications | In Progress / Validation | Amber | 2026-08-06 | TBD | 80% | Preserve OTP, MFA, retailer, and automated system-notification delivery after mail restrictions are applied. | The OTP list was provided to Mel and received by the project team; delivery validation and final allowlist confirmation remain open. | Confirm sender domains, test OTP and notification delivery, document failures, and update exceptions where justified. | Mel Gutierrez / Gemar Ermac / Yangyang Yang / Robert Moreno | Blocked OTP or system messages could interrupt retailer access and warehouse operations. | Escalate failed delivery for a business-critical system or retailer account. | Email thread: OTP list and validation updates through 8-Sep-2026
7 | Individual Retailer OTP Accounts | In Progress / Action Required | Amber | 2026-08-06 | TBD | 75% | Retain only the individual accounts required by retailers that do not accept shared or distribution addresses. | Walmart-related and other retailer accounts may require unique addresses; required accounts are being identified and protected. | Finalize account ownership, allowlist required senders, maintain approved forwarding, and migrate former-employee registrations where possible. | Gemar Ermac / Mel Gutierrez / Routing Team / Adam Li | Deactivation or unclear ownership could stop OTP delivery and create audit issues. | Approve exceptions only with a named business owner and documented operational need. | Email thread: retailer OTP and legacy-account actions through 8-Sep-2026
8 | Blocked-Mail Monitoring and Alerts | In Progress / Validation | Amber | 2026-08-31 | TBD | 80% | Detect messages blocked specifically by the UNIS.CO mail-flow restriction and support timely remediation. | Outbound monitoring and alerting are configured; confirmation that policy-specific blocks are captured remains pending. | Run controlled tests, verify alerts contain actionable details, define triage ownership, and document the escalation path. | Yangyang Yang / Network Support / Email Team | Undetected blocked mail may delay customer or operational communication. | Review alert evidence before declaring monitoring complete. | Email thread: outbound monitoring and blocked-message validation updates
9 | Shared Mailbox Archiving, Licensing and Defender | Completed / Monitor | Green | 2026-08-06 | 2026-08-31 | 100% | Protect shared mailboxes and maintain capacity, retention, and licensing required for reliable operations. | Auto-archiving was enabled where required; Exchange Online Plan 2 and Defender coverage were confirmed for the shared-mailbox environment. | Monitor mailbox capacity and archive growth; review licensing and protection coverage after mailbox inventory changes. | Email Team / Mike Wang | Capacity growth or an unlicensed mailbox could affect retention, availability, or protection. | No immediate escalation; review exceptions during the next mailbox health check. | Email thread: shared mailbox capacity, archiving, licensing, and Defender updates
10 | Business Readiness and Go/No-Go Review | In Progress / Pending Sign-Off | Amber | 2026-08-31 | TBD | 70% | Confirm readiness across Operations, Accounting, IT, Customer Service, and applicable UNIS and ITEM teams. | Coordination scope was expanded beyond one group; remaining mailbox, OTP, ticketing, and business workflow validations are being consolidated. | Collect business confirmations, document open gaps, and conduct a final readiness review with accountable stakeholders. | Robert Moreno / Gemar Ermac / Patrick Pogoy / Business Teams | Incomplete testing by a business group could leave an unrecognized operational gap. | Require named sign-off or a documented exception for each critical workflow. | Email thread: expanded business-readiness coordination through 8-Sep-2026
11 | Ticketing BCP and Operational Contingency | In Progress / High Priority | Red | 2026-08-06 | TBD | 75% | Maintain customer communication and service operations during a major ticketing outage. | A three-AZ Kubernetes architecture reduces infrastructure failure risk; the team is defining operational fallback and continuity procedures. | Finalize outage roles, phone and alternate-channel procedures, incident communication, duplicate handling, recovery validation, and test evidence. | Lex Yang / Technical Team / Mary Smothers / Robert Moreno | A prolonged ticketing outage could affect response times, SLAs, shipping and receiving, and customer commitments. | Confirm the operational contingency before final production approval. | Email thread: production readiness and BCP/DR discussions through 8-Sep-2026
12 | AWS Regional Resiliency and DR Decision | Decision Pending | Red | 2026-08-06 | TBD | 75% | Determine whether residual regional-outage risk is acceptable or requires cross-region disaster recovery. | Current production design spans three availability zones but has no secondary AWS region; leadership risk acceptance is still required. | Document current resiliency, quantify residual risk, obtain leadership decision, and prepare a multi-region design and cost only if required. | Mike Wang / Lex Yang / Technical Team / Leadership | A regional AWS outage could make the ticketing platform unavailable despite multi-AZ protection. | Leadership to accept the residual risk with contingency or authorize cross-region DR planning. | Email thread: AWS resiliency, residual risk, and leadership decision updates
13 | Seven Remaining Account Exceptions | In Progress / Final Correction | Amber | 2026-09-11 | TBD | 70% | Resolve the final account-data exceptions before full rollout or closure. | Yangyang's validation found four accounts with inconsistent UPN/email values and three accounts that do not use the unis.co domain. | Billy and Yangyang to correct all seven accounts, revalidate against the active-employee list, and document closure evidence. | Billy Rivas / Yangyang Yang | Uncorrected accounts could cause access, routing, or migration omissions. | Close only after all seven exceptions are corrected and independently revalidated. | IT Network Team Meeting Notes, 11-Sep-2026 PST

## UNIS ITEM- eHub integration
# | Project / Workstream | Status | RAG Status | Start Date | Completion Date | % of Completion | Core Objective | Current Progress | Key Next Steps | Owners / Direct Responsible Individual | Key Risks / Blockers | Management Attention | Source / Notes
1 | UNIS/ITEM-eHub Carrier Integration | In Progress / External Inputs Pending | Amber | 2026-09-02 | TBD | 70% | Integrate eHub carrier services with UNIS/ITEM workflows and validate initial customer and carrier pilots. | Vesync and Top Street Performance are the preferred first customer candidates. Regional-carrier options are being requested for Anaheim and Santa Fe Springs. The requested USPS rate information has not yet been received from the USPS sales representative. Current carriers are UPS, FedEx, AmazonShip, DHL, USPS, UniUni, and Passport Global for international shipments. | Confirm regional-carrier options; align before customer outreach; obtain and compare USPS rates; validate USPS billing/account compatibility; complete UPS/FedEx controlled-pilot prerequisites; define the WMS method for retrieving active eHub services; confirm onboarding, support, integration, Operations, and Finance owners. | Jody Crouse / Sara Chen / Katie Petty / Gene Kwon / Stacy / Robert M / eHub Technical Team / UNIS Technical Team / Operations / Finance-AP | USPS rate validation is blocked by external information. Regional coverage, rates, pickup, volume, transit, billing, account configuration, and customer interest remain unconfirmed. High-volume carrier pilots create operational and financial risk without controlled testing. | Approve the initial customer/facility, billing model, rates, commercial documents, technical ownership, and test evidence before production enablement. | eHub email thread: Executive Summary 2-Sep-2026; Sara Chen updates 4-Sep-2026 and latest follow-up; Jody Crouse updates 10-Sep-2026 and latest candidate recommendation.